## GANTT
PROJECT CROSSIT SAFER
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
Year | 2019 | [11 empty] | 2020 | [11 empty] | 2021
Project months | jan | feb | mar | apr | may | jun | jul | aug | sept | oct | nov | dec | jan | feb | mar | apr | may | jun | jul | aug | sept | oct | nov | dec | jan | feb | mar | apr | may | jun | jul | aug | sept | oct | nov | dec
WP1: Project Management
Activity 1.1-Comitato di Gestione del progetto / Upravni odbor projekta
Activity 1.2-Gestione, amministrazione e rendicontazione del progetto / Upravljanje, administrativno vodenje in poročanje projekta
Activity 1.3-Monitoraggio e valutazione del progetto / Nadzor in evalvacija projekta
WP2: Communication
Activity 2.1– Eventi\Dogodki
Activity 2.2– Campagna pubblicitaria\Oglaševalska kampanja
Activity 2.3- Brochure e depliant\ Brošure in letaki
Activity 2.4– Pubblicazioni\ Tiskovine
Activity 2.5 - Sito web\ Spletna stran
Activity 2.6- Account social media\Socialna omrežja
Activity 2.7- Newsletter o direct mailing\Newsletter ali direktni mailing
Activity 2.8 - Conferenze stampa\ Novinarske konference
Activity 2.9- Altre relazioni con i media\Drugi odnosi z javnostmi
WP 3.1 Joint cross-border protocols of intervention
Activity 3.1.1-Analyses of current state of the art and needs
Activity 3.1.2-Joint cross-border protocols
Activity 3.1.3-Crossborder/crossregional emergency plans and standard operational procedure for the crossborder area
Activity 3.1.4-Rescue Contingents (modules)
WP 3.2 Harmonization of civil protection governance in cross-border area
Activity 3.2.1-Identificazione e monitoraggio in tempo reale delle emergenze
Activity 3.2.2-Valutazione del rischio sismico
Activity 3.2.3- Rischio incendi boschivi e di Interfaccia urbano/rurale
Activity 3.2.4-Metodi speditivi di quantificazione e mappatura dei danni
Activity 3.2.5-Condivisione e sviluppo di sistemi informativi
WP 3.3 TRAINING, EDUCATION, AWARENESS RAISING
Activity 3.3.1-Training programs for CP
Activity 3.3.2-Trainings for CP
Activity 3.3.3-Specialized response units
Activity 3.3.4-Information campaign and trainings for population resilience